## Spec
Area | Feature ID | User story | Expected behavior (from code) | Status | Defects | Type | Test method | Iteration | Notes / source | Open questions
Root CLI | ROOT-001 | As a CLI user I want to start Hex with an optional prompt so I can begin an AI session. | `hex [prompt]` accepts arbitrary args, joins them with spaces, initializes shutdown/coordinator/logging/event/cost tracking, then dispatches to print mode when `--print` is set or interactive TUI otherwise. | Tested-Pass | - | - | CLI smoke + unit tests | 1 | cmd/hex/root.go:102 runRoot; cmd/hex/root.go:268 joinArgs
Root CLI | ROOT-002 | As a scripted user I want non-interactive print mode so I can run one-off prompts. | `--print/-p` routes to print mode; default mux print and legacy print both require a prompt unless legacy image input is supplied. | Tested-Pass | - | - | CLI smoke with isolated config where possible | 1 | cmd/hex/root.go:123; cmd/hex/print.go:22 runPrintMode; cmd/hex/mux_runner.go:23
Root CLI | ROOT-003 | As an interactive user I want Hex to open a terminal UI when no print flag is used. | Interactive mode validates resume flag conflicts, opens SQLite storage, resolves provider/model/template/AGENTS.md context, creates or resumes a conversation, registers tools/skills/commands/MCP, and starts a Bubble Tea program. | Tested-Pass | - | - | Go tests + guarded TUI smoke | 1 | cmd/hex/root.go:279 runInteractive; cmd/hex/root.go:655 tea.NewProgram
Root CLI | ROOT-004 | As a user I want setup to run automatically only when needed. | On first run, non-print mode invokes `RunWizard`; if cancelled it exits nil, and print mode skips first-run wizard. | Tested-Pass | - | - | Unit/CLI smoke | 1 | cmd/hex/root.go:250; cmd/hex/wizard.go
Root CLI | ROOT-005 | As a user I want CLI version output. | Cobra root command has `Version` set from the package-level `version` variable, so `hex --version` is handled by Cobra without entering `runRoot`. | Tested-Pass | - | - | CLI smoke | 1 | cmd/hex/root.go:102
Root CLI | ROOT-006 | As an interactive user I want to continue the latest conversation from the root command. | `--continue` loads the most recently updated conversation, restores its model/messages, or prints `No previous conversations found, starting new session` and creates a new session when none exist. | Tested-Pass | - | - | CLI smoke with temp db | 1 | cmd/hex/root.go:134; cmd/hex/root.go:374
Root CLI | ROOT-007 | As a user I want to choose the database path. | `--db-path` defaults to the platform default path and is passed to `openDatabase` by root, history, resume, favorite, favorites, and export commands. | Tested-Pass | - | - | CLI smoke with temp db | 1 | cmd/hex/root.go:136; cmd/hex/storage.go; cmd/hex/history.go; cmd/hex/export.go
Root CLI | ROOT-008 | As a user I want verbose mode when advertised. | `--verbose` raises logging to debug level without setting `HEX_DEBUG`; `--debug` remains the stronger mode that also enables debug environment behavior. | Verified | - | - | Unit test | 1 | cmd/hex/root.go:121; cmd/hex/root.go:initializeLogging; cmd/hex/logging_integration_test.go:TestVerboseEnablesDebugLogLevel | Verified by go test ./cmd/hex -run TestVerboseEnablesDebugLogLevel.
Root CLI | ROOT-009 | As a user I want a custom system prompt in print mode. | `--system-prompt` is appended to the default prompt in mux print mode and appended after default identity in legacy print unless a replace-mode spell overrides it. | Tested-Fail | API-gated behavior not executed because ANTHROPIC_API_KEY is absent. | Logistical | API-gated print smoke | 3 | cmd/hex/root.go:149; cmd/hex/mux_runner.go:91; cmd/hex/print.go:158 | CAPPED after 3 loop passes: cannot verify live system-prompt behavior without ANTHROPIC_API_KEY.
Root CLI | ROOT-010 | As a scripted user I want to limit enabled tools. | `--tools` filters mux print tools directly; in legacy print it is converted into `allowedTools` only when `--allowed-tools` was not set. | Tested-Fail | API-gated tool filtering not executed against a live model because ANTHROPIC_API_KEY is absent. | Logistical | CLI/API-gated smoke | 3 | cmd/hex/root.go:148; cmd/hex/mux_runner.go:251; cmd/hex/print_tools.go:16 | CAPPED after 3 loop passes: cannot verify live tool filtering without ANTHROPIC_API_KEY.
Logging | LOG-001 | As a user I want configurable log level and format. | `--log-level` is parsed into logger level; `--log-format json` selects JSON logs and other values use text formatting. | Tested-Pass | - | - | CLI smoke with log file | 1 | cmd/hex/root.go:139; cmd/hex/root.go:683 initializeLogging
Config | CFG-001 | As a user I want provider selection from flags or config with a default. | Provider name is resolved as flag, then config, then `anthropic`; supported providers are anthropic, openai, gemini, openrouter, and ollama. | Tested-Pass | - | - | Unit tests / CLI error smoke | 1 | cmd/hex/root.go:313; cmd/hex/root.go:319
Config | CFG-002 | As a user of non-Anthropic providers I want a clear model requirement. | Interactive mode and legacy print mode require `--model` for non-Anthropic providers and return an error with example model names when missing. | Tested-Pass | - | - | CLI error smoke | 1 | cmd/hex/root.go:354; cmd/hex/print.go:54
Config | CFG-003 | As an Anthropic TUI user I want API key validation before session start. | TUI mode only supports Anthropic; it loads provider config, overrides API key from `ANTHROPIC_API_KEY`, and errors if no key is configured. | Tested-Pass | - | - | CLI error smoke | 1 | cmd/hex/root.go:467; cmd/hex/root.go:481
Config | CFG-004 | As a user I want debug logging without corrupting the TUI. | `--debug` sets `HEX_DEBUG=1`, writes logs to `--log-file` or `/tmp/hex-debug.log`, and only writes debug logs to stderr in print mode. | Tested-Pass | - | - | CLI smoke + file check | 1 | cmd/hex/root.go:683 initializeLogging
Permissions | PERM-001 | As a user I want permission modes for tool execution. | `--permission-mode` parses `ask`, `auto`, or `deny`; ask requires prompting, auto allows, deny blocks. Invalid modes error. | Tested-Pass | - | - | Unit tests / CLI smoke | 1 | cmd/hex/root.go:750 createPermissionChecker; internal/permissions/mode.go:32 ParseMode; internal/permissions/checker.go:36 Check
Permissions | PERM-002 | As a user I want allow and deny lists to constrain tools. | `--allowed-tools` and `--disallowed-tools` build permission rules; tools not in an allow list or present in a deny list are blocked before mode handling. | Tested-Pass | - | - | Unit tests | 1 | cmd/hex/root.go:759; internal/permissions/checker.go:42 Check
Permissions | PERM-003 | As a legacy user I want old permission bypass flag compatibility. | `--dangerously-skip-permissions` changes mode to `auto` and logs a deprecation warning. | Tested-Pass | - | - | CLI smoke | 1 | cmd/hex/root.go:744 createPermissionChecker
Storage | STOR-001 | As a user I want conversations persisted locally. | Opening a database enables foreign keys, enables WAL journal mode, and runs embedded migrations before use. | Tested-Pass | - | - | Go tests + CLI smoke with temp db | 1 | internal/storage/schema.go:39 OpenDatabase
Storage | STOR-002 | As a user I want new conversations recorded with metadata. | Creating a conversation generates a UUID when missing, defaults timestamps to now and provider to Anthropic, then inserts title/provider/model/system prompt/timestamps. | Tested-Pass | - | - | Go tests | 1 | internal/storage/conversations.go:27 CreateConversation
Storage | STOR-003 | As a user I want messages saved in order. | Creating a message generates a UUID when missing, inserts role/content/tool calls/metadata, and updates parent conversation timestamp in the same transaction; listing orders by created_at ascending. | Tested-Pass | - | - | Go tests | 1 | internal/storage/messages.go:24 CreateMessage; internal/storage/messages.go:88 ListMessages
History | HIST-001 | As a user I want recent conversation history. | `hex history` opens the configured db, fetches recent history up to `--limit` default 20, prints empty-state guidance when none, and shows relative time, truncated preview, and conversation ID. | Tested-Pass | - | - | CLI smoke with seeded temp db | 1 | cmd/hex/history.go:53 runHistory; cmd/hex/history.go:128 displayHistoryEntry
History | HIST-002 | As a user I want to search history. | `hex history search <query>` uses full-text search up to `--limit`, prints no-results guidance if empty, and formats matching entries like recent history. | Tested-Pass | - | - | CLI smoke with seeded temp db | 1 | cmd/hex/history.go:89 runHistorySearch
Resume | RES-001 | As a user I want to resume the most recent conversation. | `hex resume --last` loads the latest conversation or errors if none, validates existence, loads messages, prints session metadata to stderr, and continues interactive mode. | Tested-Pass | - | - | CLI smoke with seeded temp db | 1 | cmd/hex/resume.go:62 runResume | Full interactive continuation requires terminal/API conditions.
Resume | RES-002 | As a user I want to resume a specific conversation by ID. | `hex resume <conversation-id>` validates the conversation, loads ordered messages into a UI model, preserves favorite status, and continues interactive mode. | Tested-Pass | - | - | CLI smoke with seeded temp db | 1 | cmd/hex/resume.go:58; cmd/hex/resume.go:94
Resume | RES-003 | As a user I want a picker when resuming without arguments. | `hex resume` lists up to 20 recent conversations through `conversationsForPicker`, passes them to `ui.NewSessionPicker` in alt-screen mode, and the picker returns the selected conversation ID on Enter or an empty selection on Esc/q cancel. | Verified | - | - | TUI/unit tests | 1 | cmd/hex/resume.go:73; cmd/hex/resume.go:132 showConversationPicker; internal/ui/session_picker.go:47 NewSessionPicker | Verified by go test ./cmd/hex -run TestConversationsForPickerLimitsToTwenty and go test ./internal/ui -run 'TestSessionPickerSelectsHighlightedConversation¦TestSessionPickerCancelLeavesSelectionEmpty'.
Favorites | FAV-001 | As a user I want to toggle a conversation as favorite. | `hex favorite <conversation-id>` loads the conversation, toggles `is_favorite`, updates `updated_at`, and prints marked/removed confirmation. | Tested-Pass | - | - | CLI smoke with temp db | 1 | cmd/hex/favorites.go:13; internal/storage/conversations.go:139 SetFavorite
Favorites | FAV-002 | As a user I want to list favorite conversations. | `hex favorites` prints an empty state when none; otherwise prints count, title truncated to 60 chars, ID, model, and relative update time for favorites ordered by updated_at descending. | Tested-Pass | - | - | CLI smoke with temp db | 1 | cmd/hex/favorites.go:50; internal/storage/conversations.go:148 ListFavorites
Export | EXP-001 | As a user I want to export conversations as Markdown, JSON, or HTML. | `hex export <conversation-id>` accepts `--format markdown¦md¦json¦html¦htm`, opens storage, writes to stdout by default or `--output`, and errors on unknown format. | Tested-Pass | - | - | CLI smoke with temp db | 1 | cmd/hex/export.go:25 runExport; internal/export/exporter.go
Export | EXP-002 | As a user writing an export file I want confirmation. | When `--output` is provided, the export file is created/truncated and a success message is written to stderr after export succeeds. | Tested-Pass | - | - | CLI smoke | 1 | cmd/hex/export.go:69; cmd/hex/export.go:82
Setup | SETUP-001 | As a user I want to re-run configuration setup. | `hex setup` runs `RunWizard`; cancellation prints `Setup cancelled.` and returns nil, success prints `Setup complete! Run 'hex' to start chatting.` | Tested-Pass | - | - | Manual/TUI guarded test | 1 | cmd/hex/setup.go:12 | Wizard choices need separate TUI verification.
Templates | TMPL-001 | As a user I want to list session templates. | `hex templates` and `hex templates list` load YAML templates from `~/.hex/templates`, print a creation example when none exist, or sorted template metadata and `hex --template <name>` usage. | Tested-Pass | - | - | CLI smoke with isolated HOME | 1 | cmd/hex/templates.go:16; cmd/hex/templates.go:37 runTemplatesList
Templates | TMPL-002 | As a user I want to start with a named template. | `--template` loads by name from `~/.hex/templates`; missing template errors with available names when any exist. TUI applies system prompt, model, title, and initial messages. | Tested-Pass | - | - | CLI smoke/unit tests | 1 | cmd/hex/root.go:331; cmd/hex/templates.go:100 loadTemplateByName
Templates | TMPL-003 | As a template author I want validation. | Template YAML requires `name`; initial message roles must be user/assistant/system and content cannot be empty. | Tested-Pass | - | - | Go tests | 1 | internal/templates/types.go:27 Validate; internal/templates/loader.go:17 LoadTemplate
MCP | MCP-001 | As a user I want to add MCP servers. | `hex mcp add <name> <command> [args...]` disables flag parsing, stores a stdio server config in the project registry, saves it, and prints command/config path. | Tested-Pass | - | - | CLI smoke in temp dir | 1 | cmd/hex/mcp.go:23; cmd/hex/mcp.go:68 runMCPAdd
MCP | MCP-002 | As a user I want to list configured MCP servers. | `hex mcp list` loads the project MCP registry, prints empty-state guidance when no servers exist, otherwise prints name, transport, full command, total, and config path. | Tested-Pass | - | - | CLI smoke in temp dir | 1 | cmd/hex/mcp.go:42; cmd/hex/mcp.go:104 runMCPList
MCP | MCP-003 | As a user I want to remove an MCP server. | `hex mcp remove <name>` loads the registry, removes the named server, saves, and prints removal confirmation. | Tested-Pass | - | - | CLI smoke in temp dir | 1 | cmd/hex/mcp.go:55; cmd/hex/mcp.go:133 runMCPRemove
Plugins | PLUG-001 | As a user I want to install plugins. | `hex plugin install <source>` creates the default plugin registry, calls `Install(source)`, and prints progress and success. | Tested-Pass | - | - | Unit/CLI with local fixture | 1 | cmd/hex/plugin.go:21; cmd/hex/plugin.go:89 runPluginInstall | Remote Git install should not be exercised without network fixture.
Plugins | PLUG-002 | As a user I want to list plugins. | `hex plugin list¦ls` prints empty-state install guidance or a tabular NAME/VERSION/STATUS/DESCRIPTION list, truncating descriptions over 50 chars. | Tested-Pass | - | - | CLI smoke with isolated HOME | 1 | cmd/hex/plugin.go:46; cmd/hex/plugin.go:117 runPluginList
Plugins | PLUG-003 | As a user I want plugin lifecycle controls. | `install`, `uninstall¦remove¦rm`, `enable`, `disable`, `update`, and `show¦info` delegate to the default registry and print success or detailed plugin fields. | Tested-Pass | - | - | CLI/unit with fixture | 1 | cmd/hex/plugin.go:38; cmd/hex/plugin.go:153; cmd/hex/plugin.go:211
Skills | SKILL-001 | As a user I want built-in, user, project, and plugin skills available to the agent. | Skill initialization locates built-in dirs, includes plugin paths, loads all skills, registers each unique skill, warns on failures, and exposes a `Skill` tool adapter. | Tested-Pass | - | - | Go tests | 1 | cmd/hex/skills.go:14 initializeSkills; internal/skills/loader.go
Slash Commands | CMD-001 | As a user I want slash commands available to the agent and autocomplete. | Command initialization locates built-in command dirs, includes plugin paths, loads and registers commands, exposes a slash-command tool, and passes command names/descriptions to the UI model. | Tested-Pass | - | - | Go tests | 1 | cmd/hex/commands.go:14 initializeCommands; cmd/hex/root.go:621
Slash Commands | CMD-002 | As a user I want `/brainstorm` to guide design exploration. | Built-in `brainstorm.md` defines a Socratic design workflow with understanding, alternatives, refinement, validation, and structured output around an optional topic argument. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/brainstorm.md
Slash Commands | CMD-003 | As a user I want `/plan` to create an implementation plan. | Built-in `plan.md` asks the agent to analyze requirements, break down work, specify file-level tasks, plan tests, and output dependencies/success criteria. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/plan.md
Slash Commands | CMD-004 | As a user I want `/debug` to investigate issues systematically. | Built-in `debug.md` defines reproduce/evidence/trace/root-cause, pattern analysis, hypothesis testing, and implementation phases around an optional issue argument. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/debug.md
Slash Commands | CMD-005 | As a user I want `/test` to drive TDD. | Built-in `test.md` defines red-green-refactor behavior for a target and optional test type. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/test.md
Slash Commands | CMD-006 | As a user I want `/review` for code review. | Built-in `review.md` asks the agent to inspect status/diff, then review correctness, readability, maintainability, testing, security, performance, architecture, and breaking changes. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/review.md
Slash Commands | CMD-007 | As a user I want `/commit` to prepare a commit. | Built-in `commit.md` asks the agent to inspect git status/diff/staged diff, run a quality checklist, inspect recent commit style, and craft conventional commit output. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/commit.md
Slash Commands | CMD-008 | As a user I want `/refactor` for safe refactoring. | Built-in `refactor.md` requires tests/baseline understanding, states the golden rule of changing behavior or structure but not both, and guides smell identification and incremental refactoring. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/refactor.md
Slash Commands | CMD-009 | As a user I want `/document` to generate documentation. | Built-in `document.md` guides code comments, API docs, guides, and architecture documentation around optional target/type arguments. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/document.md
Slash Commands | CMD-010 | As a user I want `/help` to show slash-command and keyboard help. | Built-in `help.md` lists available slash commands, implemented keyboard shortcuts, tool approval keys, tips, and project link; help now documents Ctrl+H/Ctrl+R/Tab view switching/typewriter/favorite behavior from the TUI update path. | Verified | - | - | Static slash-help regression test | 1 | commands/help.md; internal/ui/update.go; cmd/hex/help_command_test.go | Verified by go test ./cmd/hex -run TestHelpCommandDocumentsImplementedKeyBindings.
Slash Commands | CMD-011 | As a user I want `/spell` to list or switch spells. | Built-in `spell.md` renders list/reset/off/cast spell prompts and documents built-in spell names, layer/replace modes, and print-mode usage. | Tested-Pass | - | - | Slash-command tool test | 1 | commands/spell.md
Spells | SPELL-001 | As a user I want named spells to alter agent behavior. | `--spell` loads a spell by name from project, user, or embedded builtin sources; `--spell-mode` can override mode; replace mode uses only spell prompt, layer mode appends to existing prompt. | Tested-Pass | - | - | Go tests / print smoke | 1 | cmd/hex/spells_init.go:60 getSpellWithMode; internal/spells/loader.go:150; internal/spells/applicator.go:30
Spells | SPELL-002 | As a spell author I want spell directories parsed predictably. | A spell directory must contain `system.md`; optional `config.yaml` sets mode/config; optional `tools/*.yaml` create tool overrides; invalid spell validation aborts that spell. | Tested-Pass | - | - | Go tests | 1 | internal/spells/parser.go:17 ParseSpellDirectory
Tools | TOOL-001 | As an agent I want to read files safely. | `read_file` requires path, supports optional byte offset and limit, and returns file contents or expected failure result. | Tested-Pass | - | - | Go tests / print-mode tool smoke | 1 | internal/tools/read_tool.go; internal/tools/registry.go:68
Tools | TOOL-002 | As an agent I want to write files with explicit modes. | `write_file` requires path/content and supports create, overwrite, or append, defaulting to create. | Tested-Pass | - | - | Go tests with temp dir | 1 | internal/tools/write_tool.go; internal/tools/registry.go:87
Tools | TOOL-003 | As an agent I want exact string file edits. | `edit` performs exact replacements, requiring a unique match unless `replace_all` is true. | Tested-Pass | - | - | Go tests with temp dir | 1 | internal/tools/edit_tool.go; internal/tools/registry.go:220
Tools | TOOL-004 | As an agent I want shell command execution. | `bash` executes a subprocess with command, optional timeout seconds, working directory, and background mode. | Tested-Pass | - | - | Go tests / CLI smoke | 1 | internal/tools/bash_tool.go; internal/tools/registry.go:106
Tools | TOOL-005 | As an agent I want to retrieve and stop background shell jobs. | `bash_output` retrieves output from a background shell by bash_id with optional regex filter; `kill_shell` kills a running background shell by shell_id. | Tested-Pass | - | - | Go tests | 1 | internal/tools/bash_output_tool.go; internal/tools/kill_shell_tool.go
Tools | TOOL-006 | As an agent I want file discovery. | `glob` finds files by glob pattern, supports recursive `**`, optional path, and sorts by modification time newest first. | Tested-Pass | - | - | Go tests with temp dir | 1 | internal/tools/glob_tool.go
Tools | TOOL-007 | As an agent I want content search. | `grep` uses ripgrep-compatible search with pattern, optional path, output modes content/files_with_matches/count, case-insensitive flag, context flags, glob filter, and file type filter. | Tested-Pass | - | - | Go tests with temp dir | 1 | internal/tools/grep_tool.go; internal/tools/registry.go:142
Tools | TOOL-008 | As an agent I want to ask structured questions. | `ask_user_question` gathers information through multiple-choice questions using the tool contract. | Tested-Pass | - | - | Go tests | 1 | internal/tools/ask_user_question_tool.go
Tools | TOOL-009 | As an agent I want structured task tracking. | `todo_write` creates and manages structured todo lists for progress tracking. | Tested-Pass | - | - | Go tests | 1 | internal/tools/todo_write_tool.go
Tools | TOOL-010 | As an agent I want web research tools. | `web_fetch` fetches URL content and processes it with a prompt; `web_search` searches DuckDuckGo and returns results. These tools are registered in interactive and legacy print setup, but not in mux print's base tool list. | Tested-Pass | - | - | Go tests / network-gated smoke | 1 | internal/tools/web_fetch_tool.go; internal/tools/web_search_tool.go; cmd/hex/root.go:535; cmd/hex/mux_runner.go:236 | Network behavior may be environment-dependent.
Tools | TOOL-011 | As an agent I want to delegate complex work. | `task` launches a sub-agent with prompt, description, subagent_type, optional model, and optional resume flag; valid subagent types come from `subagents.ValidSubagentTypes()`. | Tested-Pass | - | - | Go tests / guarded smoke | 1 | internal/tools/task_tool.go; internal/tools/registry.go:123
Print Mode | PRINT-001 | As a scripted user I want print-mode tool execution to continue across turns. | Legacy print mode builds a user message, registers print tools, sends tool definitions, executes tool-use turns, appends tool results, and stops on end_turn or max_tokens. | Tested-Pass | - | - | Unit/CLI with API gated | 1 | cmd/hex/print.go:89; cmd/hex/print.go:195 | External API required for full behavioral execution.
Print Mode | PRINT-002 | As a scripted user I want output formats. | Print mode supports `--output-format text¦json¦stream-json` through `formatOutput` when the model returns final content. | Tested-Fail | Output formatting through a live print-mode response not executed because ANTHROPIC_API_KEY is absent. | Logistical | Unit tests / API-gated smoke | 3 | cmd/hex/root.go:119; cmd/hex/print.go:237 formatOutput reference | Need exact `formatOutput` branch verification in loop. CAPPED after 3 loop passes: formatter unit coverage exists, but live print output formatting cannot be verified without ANTHROPIC_API_KEY.
Print Mode | PRINT-003 | As a scripted user I want multimodal input. | Legacy print mode accepts repeated `--image` paths, loads each image into content blocks, and appends text prompt when present. | Tested-Pass | - | - | Unit test / CLI error smoke | 1 | cmd/hex/root.go:138; cmd/hex/print.go:66
Print Mode | PRINT-004 | As a scripted user I want plan mode. | `--plan` wraps the first prompt with planning instructions; after first model response, it adds a user message telling the model to execute step by step. | Tested-Fail | Plan-mode live two-turn execution not executed because ANTHROPIC_API_KEY is absent. | Logistical | Unit/API-gated smoke | 3 | cmd/hex/root.go:158; cmd/hex/print.go:80; cmd/hex/print.go:203 | CAPPED after 3 loop passes: cannot verify live two-turn plan-mode execution without ANTHROPIC_API_KEY.
Context | CTX-001 | As a user I want context bounded by configured token limits. | `--max-context-tokens` defaults to 180000; print mode, root interactive mode, and resume continuation create a context manager from `--context-strategy`. `keep-all` disables pruning, `prune` removes older context, and `summarize` replaces pruned older messages with a compact `Previous conversation summary` message while retaining recent context. | Verified | - | - | Go tests/static check | 1 | cmd/hex/root.go:138; cmd/hex/root.go:798 createContextManager; cmd/hex/print.go:runPrintMode; cmd/hex/interactive.go:continueInteractiveWithModel; internal/convcontext/manager.go:SummarizeContext | Verified by go test ./internal/convcontext -run TestManagerSummarizeStrategyAddsSummaryForPrunedMessages and go test ./cmd/hex -run 'TestContinueInteractiveUsesContextStrategyFactory¦TestEffectiveMaxTurnsUsesConfiguredFlag'.
Context | CTX-003 | As a user I want project memory loaded into print-mode prompts. | Print modes call `loadProjectContext`, which loads `.hex/project.json`, regenerates and saves it when missing/stale after 7 days or when `--refresh-memory` is set, and appends project context to the system prompt. | Tested-Pass | - | - | CLI/static check | 1 | cmd/hex/root.go:157; cmd/hex/print.go:514 loadProjectContext; cmd/hex/mux_runner.go:103
Events | EVT-001 | As an operator I want session events recorded. | Root startup creates a temp `hex_events_*.jsonl` event store, sets `HEX_AGENT_ID` to `root` if absent, records `SessionStart`, and closes on exit; `HEX_DEBUG` prints replay/visualize hints. | Tested-Pass | - | - | CLI smoke with debug env | 1 | cmd/hex/root.go:186
Cost | COST-001 | As an operator I want cost summaries. | Root initializes global cost tracking and on exit prints session cost to stderr when tracked cost for `HEX_AGENT_ID` is greater than zero; interactive also calls `cost.PrintCostSummary`. | Tested-Fail | Live usage/cost summary not executed because ANTHROPIC_API_KEY is absent. | Logistical | Unit/API-gated smoke | 3 | cmd/hex/root.go:227; cmd/hex/root.go:667 | CAPPED after 3 loop passes: cannot verify nonzero live usage/cost summary without ANTHROPIC_API_KEY.
Visualization | VIZ-001 | As an operator I want to visualize event files. | `hex visualize <event-file>` checks file existence, finds `hexviz` on PATH or `bin/hexviz`, passes `-events`, `-view`, optional agent/type/html flags, and streams stdout/stderr. | Tested-Pass | - | - | CLI smoke with sample events | 1 | cmd/hex/visualize.go:15; cmd/hex/visualize.go:46 runVisualize
Visualization | VIZ-002 | As an operator I want standalone visualization modes. | `hexviz` loads JSONL events, optionally filters by agent/type, renders tree, timeline, or cost view, errors on unknown view, and optionally exports HTML. | Tested-Pass | - | - | CLI smoke with sample events | 1 | cmd/hexviz/main.go:69
Replay | REPLAY-001 | As an operator I want to replay event timelines. | `hex replay <event-file>` checks file existence, finds `hexreplay` on PATH or `bin/hexreplay`, passes event/agent/type args, and streams stdout/stderr. | Tested-Pass | - | - | CLI smoke with sample events | 1 | cmd/hex/replay.go:15; cmd/hex/replay.go:39 runReplay
Replay | REPLAY-002 | As an operator I want standalone replay filtering. | `hexreplay` reads JSONL events, skips unparsable lines with log warnings, filters by exact agent or child-agent prefix and exact event type, prints timestamp/type/agent rows, and total count. | Tested-Pass | - | - | CLI smoke with sample events | 1 | cmd/hexreplay/main.go:19
Replay | REPLAY-003 | As an operator I want verbose replay details. | `hexreplay -v` prints indented event data JSON when present and parent ID lines when present, in addition to the normal timeline rows. | Tested-Pass | - | - | CLI smoke with sample events | 1 | cmd/hexreplay/main.go:23; cmd/hexreplay/main.go:68
TUI | TUI-001 | As an interactive user I want a full terminal chat UI. | Interactive mode constructs `ui.Model` with conversation/model, services, API client, tool registry/executor, slash commands, context manager, then runs Bubble Tea with alt-screen when stdin is a terminal. | Tested-Pass | - | - | Go UI tests + guarded terminal smoke | 1 | cmd/hex/root.go:415; cmd/hex/root.go:655; internal/ui/model.go
TUI | TUI-002 | As an interactive user I want previous messages visible after resume. | Resume and continue paths load stored messages and call `uiModel.AddMessage(role, content)` for each before launching the UI. | Tested-Pass | - | - | Go tests | 1 | cmd/hex/root.go:385; cmd/hex/root.go:403; cmd/hex/resume.go:104
TUI | TUI-003 | As a user I want slash-command autocomplete. | After command registry initialization, interactive mode sends command names and descriptions to the UI model for autocomplete. | Tested-Pass | - | - | Go UI tests | 1 | cmd/hex/root.go:621
TUI | TUI-004 | As a user I want tool approvals visible in the UI. | Interactive mode wires a permission checker into the tool executor; UI approval handling is expected to determine approvals while executor approval function itself returns true. | Tested-Pass | - | - | Go UI tests | 1 | cmd/hex/root.go:600; internal/ui/approval.go; internal/ui/overlay_tool_approval.go | Approval prompt behavior needs exact UI model verification.
Landing Page | WEB-001 | As a visitor I want the main marketing page. | Astro page `/` renders the landing-page implementation through `landing-page/src/pages/index.astro` using the shared layout and global styles. | Tested-Pass | - | - | npm build / browser smoke | 1 | landing-page/src/pages/index.astro; landing-page/src/layouts/Layout.astro
Landing Page | WEB-002 | As an alpha visitor I want the alpha page. | Astro page `/alpha` renders from `landing-page/src/pages/alpha.astro` through the shared layout. | Tested-Pass | - | - | npm build / browser smoke | 1 | landing-page/src/pages/alpha.astro; landing-page/src/layouts/Layout.astro
Build/Test | QA-001 | As a maintainer I want a full verification command. | `make verify` runs `fmt`, `vet`, `lint`, and `test`; `make test` runs `go test -v -race ./...`; `make test-short` runs short tests. | Tested-Pass | - | - | Command verification | 1 | Makefile:12; Makefile:93
Build/Test | QA-002 | As a maintainer I want visualization binaries built with the app. | `make build` depends on `build-viz`, builds `bin/hex`, and `build-viz` builds `bin/hexviz` and `bin/hexreplay`. | Tested-Pass | - | - | Command verification | 1 | Makefile:13; Makefile:105
Build/Test | QA-003 | As a maintainer I want dependency audits clean enough to trust the landing page build. | `npm audit --audit-level=high` reports high-severity vulnerabilities in the landing-page dependency tree, including Astro, Vite, Rollup, h3, devalue, defu, picomatch, and svgo advisories. | Tested-Fail | Landing dependency audit fails with 13 vulnerabilities, 8 high. | Security | npm audit --audit-level=high | 3 | landing-page/package-lock.json; npm audit output | Fix path may require dependency updates, possibly including a breaking Astro upgrade. CAPPED after 3 loop passes: npm audit remains red; remediation requires explicit permission for security dependency updates, likely including a breaking Astro upgrade.
Doctor | DOC-001 | As a user I want to check installation health. | `hex doctor` prints checks for `~/.hex`, config file, and API key; it reports pass/fail status but returns nil from the command. | Tested-Pass | - | - | CLI smoke with isolated HOME | 1 | cmd/hex/doctor.go:12; cmd/hex/doctor.go:23
Print Mode | PRINT-005 | As a scripted user I want mux print mode by default. | Print mode routes to `runPrintModeWithMux` unless `--legacy` is set; mux print rejects image paths with a message to use `--legacy`, builds mux tools, and streams text output. | Tested-Fail | Mux print live execution not executed because ANTHROPIC_API_KEY is absent. | Logistical | CLI smoke/API-gated test | 3 | cmd/hex/print.go:23; cmd/hex/mux_runner.go:23 | CAPPED after 3 loop passes: cannot verify live mux print streaming without ANTHROPIC_API_KEY.
Print Mode | PRINT-006 | As a scripted user I want stream-json output when advertised. | Legacy `formatOutput` accepts `stream-json` and writes one compact JSON response line. Mux print still does not honor `--output-format`. | Verified | - | - | Unit test for legacy formatter; mux remains covered by PRINT-005 | 1 | cmd/hex/root.go:118; cmd/hex/print.go:formatOutputTo; cmd/hex/stuck_detection_test.go:TestFormatOutputStreamJSONWritesSingleLine | Verified by go test ./cmd/hex -run TestFormatOutputStreamJSONWritesSingleLine.
Print Mode | PRINT-007 | As a scripted user I want max-turns to control print-mode loops. | `--max-turns` is registered globally; legacy print reads it through `effectiveMaxTurns`, and mux print passes it as `adapter.Config.MaxIterations` to mux `agent.Config.MaxIterations`. | Verified | - | - | Unit/static bridge tests | 1 | cmd/hex/root.go:162; cmd/hex/print.go:effectiveMaxTurns; cmd/hex/mux_runner.go:runPrintModeWithMux; internal/adapter/bootstrap.go:Config | Verified by go test ./cmd/hex -run 'TestRunPrintModeWithMuxPassesMaxTurnsToAgentConfig¦TestEffectiveMaxTurnsUsesConfiguredFlag' and go test ./internal/adapter -run 'TestNewRootAgentCarriesMaxIterations¦TestNewSubagentCarriesMaxIterations'.
Thinking | THINK-001 | As a user I want extended thinking for complex tasks. | `--thinking` enables an Anthropic mux client wrapper with `--thinking-budget`; non-Anthropic providers log a warning and ignore thinking. | Tested-Fail | Live thinking-mode execution not executed because ANTHROPIC_API_KEY is absent. | Logistical | CLI/API-gated test | 3 | cmd/hex/root.go:159; cmd/hex/mux_runner.go:69 | CAPPED after 3 loop passes: cannot verify live Anthropic thinking-mode wrapper without ANTHROPIC_API_KEY.
Tools | TOOL-012 | As a user I want tool calls controlled, cached, and observable. | Executor normalizes nil params, uses cache for read_file/grep/glob, applies permission checker and optional approval, fires pre/post tool hooks, executes the tool, and caches successful read-only results. | Tested-Pass | - | - | Go tests | 1 | internal/tools/executor.go:87; internal/tools/cache.go:149
Tools | TOOL-013 | As an agent I want the tool registry to expose stable schemas. | The registry rejects duplicate tool names, returns sorted names, retrieves by exact name, and emits API tool definitions using `GetToolSchema`. | Tested-Pass | - | - | Go tests | 1 | internal/tools/registry.go:29; internal/tools/registry.go:63
Hooks | HOOK-001 | As a user I want lifecycle shell hooks. | Hook config loads user then project `.hex/settings.json`; project event hook lists override user lists. Hooks support match filters, sync/async execution, timeouts, env injection, and failure blocking unless ignored. | Tested-Pass | - | - | Go tests / fixture smoke | 1 | internal/hooks/config.go:70; internal/hooks/engine.go:58; internal/hooks/executor.go:35
MCP | MCP-004 | As a user I want MCP tools loaded at session start. | Interactive startup loads optional `.mcp.json`; stdio mux clients list tools and register adapters, skipping name collisions. MCP tool adapters do not require approval by default. | Tested-Pass | - | - | Go tests with fixture MCP | 1 | cmd/hex/root.go:583; internal/mcp/loader.go:21; internal/mcp/tool_adapter.go:44
Subagents | SUB-001 | As an agent I want isolated delegated work. | Valid subagent types are `general-purpose`, `Explore`, `Plan`, and `code-reviewer`; executor spawns `hex --print`, sets subagent env vars, and records start/stop events. | Tested-Pass | - | - | Go tests / guarded CLI smoke | 1 | internal/subagents/types.go:52; internal/subagents/executor.go:46
Subagents | SUB-002 | As an agent I want dispatch strategies. | Dispatcher supports parallel, sequential, batch, and first-success delegation patterns over subagent tasks. | Tested-Pass | - | - | Go tests | 1 | internal/subagents/dispatcher.go:44
Suggestions | SUG-001 | As a TUI user I want input suggestions. | Suggestion detector returns up to 3 high-confidence actions from paths, URLs, search, shell-like input, write/edit/web intent. | Tested-Pass | - | - | Go tests | 1 | internal/suggestions/detector.go:217
TUI | TUI-005 | As an operator I want to send messages and receive streamed responses. | Enter sends trimmed input, persists the user message, updates title from first message, starts streaming if an API client exists; `exit`/`/exit` quits and `/clear` clears context. | Tested-Pass | - | - | Go UI tests / terminal smoke | 1 | internal/ui/update.go:32
TUI | TUI-006 | As an operator I want busy-session input queued. | When waiting for a response, messages queue up to 100; the first queued item is previewed, and Up pulls the first queued item back into input for editing. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/model.go:252 QueueMessage; internal/ui/model.go:267 PopQueue
TUI | TUI-007 | As an operator I want controlled quit behavior. | Ctrl+C clears non-empty input, cancels streaming/search/quick actions, and when idle requires a second Ctrl+C within two seconds to quit. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/update.go:32
TUI | TUI-008 | As an operator I want fullscreen help/history/tool overlays. | Ctrl+H toggles help, Ctrl+R toggles current conversation history capped at 1,000 messages with content truncated to 500 runes, and Ctrl+O toggles a tool timeline overlay. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/overlay_help.go:58; internal/ui/overlay_history.go:87; internal/ui/overlay_tool_timeline.go:126
TUI | TUI-009 | As an operator I want a command palette. | `:` launches async quick actions with built-ins read/grep/web/attach/save/export/settings/onboarding; command actions read/grep/web/attach prepare input with the action name and optional args, save/export use model behavior, and settings/onboarding return async form commands. | Verified | - | - | Go UI tests / terminal smoke | 1 | internal/ui/model.go:1361 connectQuickActions; internal/ui/model.go:1450 ExecuteQuickAction; internal/ui/quickactions.go:39 | Verified by go test ./internal/ui -run 'TestBuiltInActions¦TestModelQuickActionSettingsLaunchesSettingsForm¦TestModelQuickActionOnboardingLaunchesOnboardingForm¦TestModelQuickActionsExecute¦TestModelQuickActionReadPreparesInputTemplate¦TestModelQuickActionsWithArguments' and go test ./internal/ui.
TUI | TUI-010 | As an operator I want search mode. | `/` enters search mode when textarea is not focused; runes append and backspace deletes through `UpdateSearchQuery`, the query is matched case-insensitively against message content and content blocks, the prompt shows match count, Enter cycles the current match, and Esc/Ctrl+C exit search. | Verified | - | - | Go UI tests | 1 | internal/ui/model.go:EnterSearchMode; internal/ui/model.go:UpdateSearchQuery; internal/ui/update.go:SearchMode; internal/ui/view.go:Search prompt | Verified by go test ./internal/ui -run 'TestViewShowsSearchMode¦TestSearchModeEnterSelectsNextMatch¦TestSearchModeFindsMessageMatches¦TestSearchModeBackspace'.
TUI | TUI-011 | As an operator I want a conversation browser. | Conversation browser component renders list/preview UI with quit, Enter load preview, favorite, delete, sort, and refresh keys; preview loads recent real messages through `MessageService`, and the main History tab mounts the browser when conversation/message services are available. | Verified | - | - | Go UI tests/static reachability | 1 | internal/ui/browser/conversations.go:89; internal/ui/browser/conversations.go:418; internal/ui/model.go:894 SetServices; internal/ui/view.go:275 renderHistoryView | Verified by go test ./internal/ui -run 'TestViewRendersConversationBrowserWhenServicesAvailable¦TestViewRendersHistoryMode' and go test ./internal/ui ./internal/ui/browser.
TUI | TUI-012 | As an operator I want plugin/MCP dashboard status. | Plugin dashboard component toggles Plugin/MCP views with Tab, refreshes with r, quits with q, no longer fabricates sample rows, receives real plugin and MCP registry data through `SetIntegrationRegistries`, and renders a compact Plugin/MCP status section in Tools. | Verified | - | - | Go UI tests/static reachability | 1 | internal/ui/dashboard/plugins.go:44; internal/ui/dashboard/plugins.go:SetData; internal/ui/model.go:SetIntegrationRegistries; internal/ui/view.go:renderToolsView; cmd/hex/root.go:589 | Verified by go test ./internal/ui -run TestViewRendersIntegrationDashboardData and go test ./internal/ui ./internal/ui/dashboard ./cmd/hex.
TUI | TUI-013 | As an operator I want autocomplete beyond slash commands. | Autocomplete providers support slash commands, files, and history; the main UI detects the provider from input, opens file completions for path-like prefixes such as `./`, opens slash command completions for `/`, and feeds submitted prompts into the history provider for history completions. | Verified | - | - | Go UI tests | 1 | internal/ui/autocomplete.go:DetectProvider; internal/ui/update.go:syncAutocompleteOverlay; internal/ui/model.go:addToInputHistory; internal/ui/autocomplete_trigger_test.go | Verified by go test ./internal/ui -run 'TestModelAutocompleteTriggersForFilePaths¦TestModelAutocompleteTriggersForInputHistory'.
TUI | TUI-014 | As an operator I want to switch between TUI views. | Tab cycles Chat, History, Tools, and Intro views; History renders current conversation messages with previews, and Tools renders active/historical tool state or an empty tool-call message. | Verified | - | - | Go UI tests | 1 | internal/ui/model.go:442 NextView; internal/ui/view.go:275 renderHistoryView; internal/ui/view.go:291 renderToolsView | Verified by go test ./internal/ui -run 'TestViewRendersHistoryMode¦TestViewRendersToolsMode' and go test ./internal/ui.
TUI | TUI-015 | As an operator I want clear/save/export/typewriter/favorite shortcuts. | Ctrl+L clears screen, Ctrl+K clears conversation, Ctrl+S calls `SaveConversation`, Ctrl+E reports exported markdown length, Ctrl+T toggles typewriter mode, and Ctrl+F toggles favorite status in chat mode. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/update.go:237
TUI | TUI-016 | As an operator I want multiline input. | Ctrl+J inserts a newline and resizes input; Alt+Enter also inserts a newline before plain Enter send handling. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/update.go:346; internal/ui/update.go:360
TUI | TUI-017 | As an operator I want input history navigation. | Submitted inputs are added to input history; Up navigates older history when cursor is on the first visual row, and Down navigates newer history when cursor is on the last visual row. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/update.go:452
TUI | TUI-018 | As an operator I want mouse and keyboard scrolling. | When input is empty, `j` scrolls down and `k` scrolls up; additional mouse scroll and hover timestamp handling are implemented in the UI update path. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/update.go:432; internal/ui/update.go:576
TUI | TUI-019 | As an operator I want status context at the bottom of the screen. | Status bar renders token counts when available, permission mode indicator when executor has a checker, current view mode, and help text for common shortcuts. | Tested-Pass | - | - | Go UI tests | 1 | internal/ui/view.go:289
TUI | TUI-020 | As an operator I want token usage visualization. | The model owns a token visualization component, feeds it from `UpdateTokens`, resizes it on window-size messages, and renders compact token usage in the Tools view when token counts exist. | Verified | - | - | Go UI tests/static reachability | 1 | internal/ui/model.go:457 UpdateTokens; internal/ui/update.go:656 WindowSizeMsg; internal/ui/view.go:291 renderToolsView; internal/ui/visualization/tokens.go:40 | Verified by go test ./internal/ui -run TestViewRendersToolsMode and go test ./internal/ui.
TUI | TUI-021 | As a first-run operator I want a huh-based onboarding flow. | Onboarding form asks setup confirmation, Anthropic API key with `sk-ant-` validation, Claude model selection, tutorial offer, and sample conversation offer; it supplements the root setup wizard through the `onboarding` quick action and updates the active model when completed. | Verified | - | - | Go UI tests/static reachability | 1 | internal/ui/forms/onboarding.go:40 NewOnboardingForm; internal/ui/forms/onboarding_integration.go:21 RunOnboardingFormAsync; internal/ui/model.go:1361 connectQuickActions | Verified by go test ./internal/ui -run 'TestModelQuickActionOnboardingLaunchesOnboardingForm¦TestModelOnboardingResultUpdatesModel' and go test ./internal/ui.
TUI | TUI-022 | As an operator I want an interactive settings form. | Settings form selects model, validates Anthropic API key, validates temperature 0.0-1.0 and max tokens 256-8192, saves non-cancelled results to `~/.hex/config.toml`, and is launched from the `settings` quick action. | Verified | - | - | Go UI tests/static reachability | 1 | internal/ui/forms/settings.go:48 NewSettingsForm; internal/ui/forms/settings_integration.go:18 RunSettingsFormAsync; internal/ui/model.go:1361 connectQuickActions | Verified by go test ./internal/ui -run 'TestModelQuickActionSettingsLaunchesSettingsForm¦TestModelSettingsResultUpdatesModel' and go test ./internal/ui.
Context | CTX-002 | As a user I want long chats summarized when needed. | Context manager estimates roughly 4 chars/token, preserves system/recent/tool/error-important messages when pruning, and summarizer can call Claude Haiku and cache by content hash. | Tested-Pass | - | - | Go tests | 1 | internal/convcontext/manager.go:131; internal/convcontext/summarizer.go:31
Rate Limit | RATE-001 | As a user with parallel agents I want fewer API 429s. | Global Anthropic client limiter is a token bucket of 50 tokens refilling 1 token/minute; sync and streaming requests call `Acquire` and return context errors when blocked/cancelled. | Tested-Pass | - | - | Go tests | 1 | internal/core/client.go:32; internal/ratelimit/limiter.go:63; internal/core/stream.go:64
Landing Page | WEB-003 | As an alpha visitor I want an error state when downloads metadata fails. | `/alpha` fetches Firebase `versions.json` from the default URL or `HEX_ALPHA_VERSIONS_URL`; if fetch fails or returns non-OK, the downloads box renders a `DOWNLOAD MANIFEST UNAVAILABLE` alert and tells visitors to refresh or check GitHub. | Verified | - | - | Forced-failure Astro build + HTML assertion | 1 | landing-page/src/pages/alpha.astro; landing-page/scripts/verify-alpha-error.mjs; landing-page/package.json:test:alpha-error | Verified by npm run test:alpha-error and npm run build in landing-page.